## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | implement the ability to add the specified item to a customer's cart | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
2 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | implement the ability to add the specified amount of an item to a customer's cart | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
3 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | Core Functionality | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
4 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | GUI testing | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
5 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | Crosscut: Connectivity | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
6 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | Crosscut: Log-in Security | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
7 | R1 - I1 | 02. Purchase Items | 2.1 | add desired item to the cart | Crosscut: Log Time | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
8 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | implement the ability to change stock information after adding an item to car | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
9 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | design test cases | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
10 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | execute and document test cases | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
11 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | Core Functionality | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
12 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | GUI testing | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
13 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | Crosscut: Connectivity | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
14 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | Crosscut: Log-in Security | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
15 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | Crosscut: Log Time | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
16 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | design test cases | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo
17 | R1 - I1 | 02. Purchase Items | 2.2 | Update stock inventory | execute and document test cases | 2020-02-21 | 2020-02-28 | 100% | Mingming, Mateo

## R1 I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | implement the ability to check out with along with the desired items in a customer's cart | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
2 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Core Functionality | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
3 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | GUI Features | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
4 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Crosscut: ET - Entitlements | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
5 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Crosscut: Connectivity | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
6 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Create test cases for core functionality & GUI features | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
7 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Create test cases ET - entitlements | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
8 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Create test cases for connectivity | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
9 | R1 - I2 | 02. Purchase Items | 2.03 | Option to checkout | Execute tests and document results | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil
10 | R1 - I2 | 02. Order Processing | 3.01 | Total cart value at checkout | implement the ability to see the total value of the items in the customer's cart | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
11 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Core Functionality | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
12 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | GUI Features | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
13 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Crosscut: ET - Entitlements | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
14 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Crosscut: Connectivity | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
15 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Create test cases for core functionality & GUI features | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
16 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Create test cases ET - entitlements | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
17 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Create test cases for connectivity | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica
18 | R1 - I2 | 02. Purchase Items | 2.03 | Total cart value at checkout | Execute tests and document results | 2020-03-23 | 2020-04-01 | 100% | Mingming, Agil, Jessica