## Road Map l3
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 3/6/2020 | Iteration 2 - 4/3/2020 | Iteration 3 - 4/24/2020 | Iteration 4 - 5/15/2020
01. Product Listing | 01.01 Create webpage for product | [5 empty] | Color Appendix
| 01.02 Design GUI of product listing | [6 empty] | completed feature
| 01.03 Specify listing price | [6 empty] | I1
| 01.04 Verify product quantity available | [6 empty] | I2
02. Purchase Items | 02.01 Add desired item to cart | 5 | X |  |  |  |  | I3
| 02.02 Update stock inventory | 5 | X |  |  |  |  | I4
| 02.03 Option to checkout | 5 |  | X
| 02.04 Filter ads based on item history | 6
| 02.05 Update ads hosted on website | 7
03. Order Processing | 03.01 Total cart value at checkout | 7 |  | X
| 03.02 Enter Credit Card Info | 7 |  |  | X
| 03.03 Enter Mailing Info | 5 |  |  | X
| 03.04 Confirm Purchase | 7 |  |  |  | X
| 03.05 Order Receipt Generated | 7 |  |  |  | X
4. Delivery Monitoring | 04.01 Place order with supplier | 10
| 04.02 Ship item with carrier | 10
| 04.03 Keep tracking number on file | 10
| 04.04 Notify customer when item is delivered | 10
|  | Velocity : | 10 | 12 | 12 | 14

## Road Map l4
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 3/6/2020 | Iteration 2 - 4/3/2020 | Iteration 3 - 4/24/2020 | Iteration 4 - 5/15/2020
01. Product Listing | 01.01 Create webpage for product | [5 empty] | Color Appendix
| 01.02 Design GUI of product listing | [6 empty] | completed feature
| 01.03 Specify listing price | [6 empty] | I1
| 01.04 Verify product quantity available | [6 empty] | I2
02. Purchase Items | 02.01 Add desired item to cart | 5 | X |  |  |  |  | I3
| 02.02 Update stock inventory | 5 | X |  |  |  |  | I4
| 02.03 Option to checkout | 5 |  | X
| 02.04 Filter ads based on item history | 6
| 02.05 Update ads hosted on website | 7
03. Order Processing | 03.01 Total cart value at checkout | 7 |  | X
| 03.02 Enter Credit Card Info | 7 |  |  | X
| 03.03 Enter Mailing Info | 5 |  |  | X
| 03.04 Confirm Purchase | 7 |  |  |  | X
| 03.05 Order Receipt Generated | 7 |  |  |  | X
4. Delivery Monitoring | 04.01 Place order with supplier | 10
| 04.02 Ship item with carrier | 10
| 04.03 Keep tracking number on file | 10
| 04.04 Notify customer when item is delivered | 10
|  | Velocity : | 10 | 12 | 12 | 14

## Roles Traceability
User Roles vs. Features Matrix
Actors | 01. Product Listing |  |  |  | 02. Purchase Items |  |  |  |  | 03. Order Processing |  |  |  |  | 4. Delivery Monitoring
| 01.01 Create webpage for product | 01.02 Design GUI of product listing | 01.03 Specify listing price | 01.04 Verify product quantity available | 02.01 Add desired item to cart | 02.02 Update stock inventory | 02.03 Option to checkout | 02.04 Filter ads based on item history | 02.05 Update ads hosted on website | 03.01 Total cart value at checkout | 03.02 Enter Credit Card Info | 03.03 Enter Mailing Info | 03.04 Confirm Purchase | 03.05 Order Receipt Generated | 04.01 Place order with supplier | 04.02 Ship item with carrier | 04.03 Keep tracking number on file | 04.04 Notify customer when item is delivered
Customers
Member |  |  |  |  | X | X | X |  |  | X | X | X | X
Guest |  |  |  |  | X | X | X |  |  | X | X | X | X
Financing Group
Account Manager | [12 empty] | X | X
Financial Analyst | [12 empty] | X | X
Advertisers
Advertisement Agency | [7 empty] | X | X
Ads Analyst | [7 empty] | X | X
Suppliers
Sales Manager | [14 empty] | X | X
Inventory Management
Warehouse Manager | [14 empty] | X | X | X | X
Sales Analyst | [14 empty] | X | X | X | X

## Role Descriptions
Actors
Member
A general customer or consumer that has gone through the log-in process of the website and has created an account on DesignHub so they can purchase products listed on the website.
Guest
A general customer or consumer that either does not wish to create an account on DesignHub or does not frequent the website enough to warrant an account. Functionally the equivalent of a member.
Account Manager
Users that work for a financial institution and are required when verifying a customer's purchase information.
Financial Analyst
Similar to an account manager, an analyst works to secure the purchase process on DesignHub and flag transactions that are either invalid, incomplete, done using false information.
Advterisement Agency
A firm that functions as the overseer for the ads they wish to have hosted on DesignHub.
Ads Analyst
Working for the agencies, mentioned above, an ads analyst functions similarly to those that run ads on the radio in that they sort through and cycle relavant ads on DesignHub and update them as time goes on or an ads contract expires.
Sales Manager
The sellers on DesignHub that create and try to sell products that either they made personally or the products of the designer that they work for.
Warehouse Manager
User in charge of physically handling the products being order and shipped, they tally the products as they are being moved.
Sales Analyst
Working under the warehouse manager, a sales analyst will update the relavant information in DesignHub as products are being ordered and shipped (i.e. number of products left, out of stock, etc.).