## R1 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | implement the ability to enter and store credit card information as the customer | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
2 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | Core Functionality | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
3 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | GUI testing | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
4 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | Crosscut: Connectivity | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
5 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | Crosscut: Field Validation | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
6 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | design test cases | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
7 | R2 - I3 | 03. Order Processing | 3.2 | enter credit card info | execute and document test cases | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
8 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | implement the ability to enter and store mailing address information as the customer | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
9 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | Core Functionality | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
10 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | GUI testing | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
11 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | Crosscut: Connectivity | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
12 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | Crosscut: Field Validation | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
13 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | design test cases | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar
14 | R2 - I3 | 03. Order Processing | 3.3 | enter mailing info | execute and document test cases | 2020-04-13 | 2020-04-24 | 100% | Mingming, Agil, Zixian, Matthew, Cesar

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | implement the ability to create a webpage with all relevant info for the purchase | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
2 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | Core Functionality | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
3 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | GUI testing | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
4 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | Crosscut: Connectivity | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
5 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | Crosscut: Entitlements | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
6 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | design test cases | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
7 | R2 - I4 | 03. Order Processing | 3.4 | confirm purchase | execute and document test cases | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
8 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | implement the ability to process the purcase and create documentation for it | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
9 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | Core Functionality | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
10 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | GUI testing | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
11 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | Crosscut: Connectivity | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
12 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | Crosscut: Entitlements | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
13 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | design test cases | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica
14 | R2 - I4 | 03. Order Processing | 3.5 | order receipt generated | execute and document test cases | 2020-04-25 | 2020-05-15 | 100% | Mingming, Agil, Zixian, Matthew, Cesar, Jessica